Hyperlocal Air Quality Forecasting

+ Personalized Health Risk Alerts

Updated 20-Week Roadmap — Simplified Stack for a 3-Person Team

What changed from the original roadmap: same phase sequencing and scope discipline, but the implementation stack is simplified (Streamlit instead of React + FastAPI, Parquet/SQLite instead of PostgreSQL + PostGIS, Docker optional) to match a 3-person team and a steady, low-risk pace.

# 0. Recommended Scope Before You Start

Avoid: all of India + every pollutant + real-time traffic + satellite + GNN + TFT all at once — that is too much for 20 weeks. Instead, lock a Phase 1 target in Week 1:

| Decision | Guidance |
| --- | --- |
| City | Pune or Ahmedabad recommended for manageable station coverage (Delhi / Mumbai also possible) |
| Main pollutant | PM2.5 first — then optionally PM10, NO2, O3 |
| Forecast horizon | Start at 1 hour ahead → extend to 3 hours → 6 hours |
| Spatial resolution | 1 km × 1 km grid — don't claim street-level accuracy |

# 1. Data Source Stack

| Data Source | Purpose | Priority |
| --- | --- | --- |
| PM2.5 (CPCB / OGD) | Main target | Must-have |
| PM10, NO2, SO2, CO, O3 (CPCB / OGD) | Additional features | Recommended |
| Weather (Open-Meteo) | Temp, humidity, wind, etc. | Must-have |
| Satellite NO2 / CO (Sentinel-5P) | Spatial feature | Recommended |
| Roads (OpenStreetMap) | Spatial / traffic proxy | Recommended |
| Population / land use (OSM / Census) | Spatial features | If time remains |
| Live traffic (optional API) | Traffic features | If time remains |

## 1.1 Air quality — CPCB (primary ground truth)

India's Open Government Data platform provides real-time AQI data from monitoring stations — PM2.5, PM10, NO2, SO2, CO and O3, updated hourly.

You need: station_id, station_name, latitude, longitude, timestamp, PM2.5, PM10, NO2, SO2, CO, O3, AQI.

## 1.2 OpenAQ — backup / secondary source

Location and parameter/date-range queries, with raw measurements and hourly aggregations. CPCB stays primary; OpenAQ is backup / cross-validation so the project doesn't depend on a single source.

## 1.3 Kaggle historical dataset — initial development only

“India Air Quality Dataset 2015–2020” covers hourly/daily data across Indian cities. Use it for Week 1–3 experimentation only — not the final source. Bootstrap on it, then switch to the live CPCB/OpenAQ pipeline once your model logic works.

## 1.4 Weather — Open-Meteo

Historical weather data and forecasts, no API key required for non-commercial use. Hourly variables: temperature, humidity, precipitation, wind speed and direction.

You need: temperature, relative_humidity, wind_speed, wind_direction, precipitation, surface_pressure, cloud_cover.

## 1.5 Satellite — Sentinel-5P

TROPOMI provides NO2, CO, SO2, O3, HCHO and aerosol/cloud data via the Copernicus Data Space Ecosystem — free and open.

Important: don't start with satellite data. Build CPCB + Weather first. Only once that works, extend to CPCB + Weather + Satellite — much safer sequencing.

## 1.6 Traffic data

Don't make live traffic a core dependency. Start with proxy features derived from time and geography; add a live traffic API only if time permits.

You need: hour_of_day, day_of_week, weekday/weekend, rush_hour, road_density, distance_to_major_road, distance_to_highway, industrial_area.

MVP: traffic proxy features → Advanced (if time remains): real traffic API.

## 1.7 Storage — simplified for a 3-person team

Original plan: CSV → Parquet → PostgreSQL + PostGIS. For a 3-person team, PostGIS is more infrastructure than the project needs. Use Parquet files (or SQLite) as the working store throughout — upgrade to PostgreSQL + PostGIS only if time remains and someone wants that experience.

# 2. Simplified Implementation Stack

Phase sequencing and scope discipline from the original roadmap are kept as-is. Only the implementation layers below are simplified so one person can realistically own each without heavy cross-team coordination.

| Layer | Original plan | Recommended for 3 people |
| --- | --- | --- |
| Backend | FastAPI | Skip — logic lives directly in Streamlit / notebooks |
| Frontend | React + Leaflet / Mapbox | Streamlit + Folium / Plotly |
| Database | PostgreSQL + PostGIS | Parquet files / SQLite (upgrade only if time remains) |
| Deployment | Docker | Optional — only if time remains |
| ML | XGBoost → LSTM | Unchanged |
| Spatial | IDW → Kriging | Unchanged |
| Uncertainty | Conformal Prediction | Unchanged |

Why: FastAPI + React + PostGIS + Docker is production-grade infrastructure on top of the ML work — for 3 people that adds coordination and debugging overhead unrelated to the actual research question. Streamlit covers every dashboard requirement in Section 8 (map, forecast charts, risk engine UI) inside one Python app that a single teammate can own.

# 3. Week-by-Week Roadmap

## Phase A — Weeks 1–2: Project Foundation

Week 1 — Problem + Research

- Learn: AQI, PM2.5/PM10/NO2, spatial pollution, time-series forecasting, interpolation, uncertainty

- Decide: city, target = PM2.5, forecast = 1–6 hours, grid resolution

- Deliverables: problem statement, objectives, literature survey, system architecture, dataset plan

What your guide should see: “We have finalized the problem, target city, target pollutant and data sources.”

Week 2 — Dataset Collection

- Set up data/ with raw/{cpcb, openaq, weather, satellite}, processed/, final/

- Download historical air-quality data: station lat, lon, timestamp, PM2.5, PM10, NO2, etc.

- Download weather data for the same stations/time range

## Phase B — Weeks 3–4: Data Engineering

Week 3 — Cleaning

- Handle: missing values, duplicates, invalid readings, timestamp conversion, station consistency

- Output: clean_air_quality.csv

Week 4 — Data Integration

- Join AIR + WEATHER into a single Master Dataset, keyed by timestamp + station

- Columns: lat, lon, PM2.5, PM10, NO2, temperature, humidity, wind_speed, wind_direction, rain

## Phase C — Weeks 5–6: Exploratory Data Analysis

Week 5 — Pollution Analysis

- Graphs: PM2.5 vs time / temperature / humidity / wind; hourly pattern (e.g. rush-hour spike 7–9 AM)

Week 6 — Spatial Analysis

- Plot stations on a map, visualize higher-pollution areas

- Calculate: distance between stations, distance to roads, nearby station count

## Phase D — Weeks 7–8: Spatial Prediction (“Where?”)

Week 7 — Baseline Spatial Models

- Nearest Neighbor, then IDW (Inverse Distance Weighting) — closer stations get more influence

Week 8 — Kriging

- Implement Ordinary Kriging; compare Nearest Neighbor vs IDW vs Kriging using MAE and RMSE

- Deliverable: a hyperlocal pollution heatmap of the study area

## Phase E — Weeks 9–12: Forecasting

Week 9 — Time-Series Feature Engineering

- Lag features: PM2.5(t-1, t-2, t-3, t-6, t-12, t-24)

- Weather features: temperature, humidity, wind, rain

- Time features: hour, day, month, weekday/weekend

- Spatial features: latitude, longitude, nearby_station_PM25

Week 10 — Baseline ML Models

- Don't jump to LSTM — build Linear Regression, Random Forest, XGBoost first; compare MAE/RMSE

Week 11 — LSTM

- Sequence models: past 24 hours → LSTM → next 1 hour, then 3 hours, then 6 hours

Week 12 — Forecast Evaluation

- Compare XGBoost vs LSTM using MAE, RMSE, R², MAPE

- Report should answer: which model predicts PM2.5 best?

## Phase F — Weeks 13–14: Satellite Integration

Week 13 — Download / Process Satellite Data

- Start with NO2 only — not every Sentinel-5P variable at once

- Extract satellite values around the study region: latitude, longitude, date, NO2

Week 14 — Combine Satellite + Ground Data

- Train XGBoost on CPCB + Weather + Satellite, compare against the model without satellite

This is a strong experiment for the final report either way — improvement or no improvement is both a valid finding.

## Phase G — Weeks 15–16: Uncertainty

- Model outputs a prediction and an interval, e.g. “Predicted PM2.5 = 180, expected range 155–205, ~90% interval”

- Easy: Quantile Regression / gradient boosting quantile models

- Medium (recommended): Conformal Prediction

- Advanced: Deep ensembles / MC Dropout

Recommended: Conformal Prediction — strong uncertainty component without unnecessary complexity.

## Phase H — Weeks 17–18: Personalization & Alerts

Week 17 — Personalized Risk Engine

- Build a user profile: age group, activity level, sensitivity category

- Avoid claiming diagnosis — informational pollution-risk alerts only

- Risk engine inputs: AQI + Forecast + Uncertainty + User profile → Risk level

Week 18 — Alert System

- Current alert — “AQI is currently high”

- Forecast alert — “AQI expected to cross your threshold within 2 hours”

- Uncertainty alert — “Prediction confidence is low; expected range 170–230”

- Start with dashboard notifications; add email/browser later if time allows. Skip SMS.

## Phase I — Weeks 19–20: Dashboard, Testing & Presentation

Week 19 — Full Dashboard (Streamlit)

- Home: current AQI, PM2.5, risk level

- Map: interactive city map + AQI heatmap + monitoring stations (Folium/Plotly)

- Forecast: current, +1h through +6h

- Personal Risk: user profile → risk level → recommendation

- Model Info: model used, MAE, RMSE, prediction interval, confidence

Week 20 — Testing + Presentation

- Data handling tests: missing values, API failure, bad data

- ML tests: overfitting, data leakage, forecast accuracy

- App tests: wrong location, no nearby sensor, API unavailable

- Presentation flow: Problem → Existing limitations → Our solution → Architecture → Datasets → ML models → Results → Dashboard → Limitations → Future work

Buffer note: 20 weeks of continuous deliverables assumes no interruptions. Mentally reserve 2–3 catch-up weeks around Week 8 and Week 16 (after Spatial Prediction and Forecasting) to absorb exams and other coursework.

# 4. Final ML Pipeline

- Raw Data: CPCB/OpenAQ + Open-Meteo + Sentinel-5P

- Preprocessing → Feature Engineering

- Spatial Prediction (IDW / Kriging)  +  Time Prediction (XGBoost / LSTM)

- Future PM2.5 / AQI

- Conformal Prediction → Prediction Interval

- User Profile → Risk Engine → Alert

# 5. Recommended Repository Structure

hyperlocal-air-quality/
  data/
    raw/  (cpcb, openaq, weather, sentinel5p)
    processed/
    features/
  notebooks/
    01_data_collection.ipynb ... 10_uncertainty.ipynb
  src/
    data/  preprocessing/  spatial/
    forecasting/  uncertainty/  personalization/
  models/  (xgboost, lstm, spatial)
  app/  (Streamlit dashboard)
  tests/
  requirements.txt
  README.md

# 6. API / Data Source Summary

## Must-have

| Source | Purpose |
| --- | --- |
| CPCB / India OGD | Ground air-quality data (real-time AQI dataset) |
| OpenAQ | Air-quality measurements — validation / backup |
| Open-Meteo | Weather data; no API key required for non-commercial use |
| Sentinel-5P | Satellite atmospheric pollution data (via Copernicus) |
| OpenStreetMap | Roads, road density, industrial areas, distance to highways |

## Optional

Google Maps Routes API — use only for additional traffic/route features; not required for the first ML model.

# 7. Final Master Dataset Schema

The most important dataset in the project. After joining all sources, rows look approximately like this:

| time | lat | lon | PM2.5 | PM10 | NO2 | temp | hum | wind | sat_NO2 | target_1h |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10:00 | 18.52 | 73.85 | 85 | 120 | 42 | 30 | 65 | 3.2 | 0.0001 | 92 |
| 11:00 | 18.52 | 73.85 | 92 | 125 | 45 | 31 | 63 | 2.8 | 0.0002 | 105 |

Target column is target_PM25_1h — “what will PM2.5 be one hour from now?” Later add target_PM25_3h and target_PM25_6h.

A note on AQI vs. PM2.5: predict PM2.5 concentration first, then calculate AQI from it — PM2.5 → AQI is a defined formula, not a separate model. Pipeline: Model predicts PM2.5 → AQI calculation → AQI category. Much easier to explain in a viva.

# 8. Suggested Experiments

Running a structured set of experiments — not a single model — is what makes this look like a real research project rather than just an app.

| Model | Weather | Spatial | Satellite | MAE | RMSE |
| --- | --- | --- | --- | --- | --- |
| Baseline | No | No | No | — | — |
| XGBoost | Yes | No | No | — | — |
| XGBoost | Yes | Yes | No | — | — |
| XGBoost | Yes | Yes | Yes | — | — |
| LSTM | Yes | No | No | — | — |

Do not invent these numbers in advance — fill MAE/RMSE in after actually running each experiment.

# 9. What Is Actually Mandatory?

With 20 weeks, prioritize ruthlessly. A completed core system beats an incomplete ambitious one.

| Tier | Scope |
| --- | --- |
| Mandatory | CPCB/OpenAQ + Weather + Data cleaning + EDA + XGBoost baseline + LSTM + Spatial interpolation + Streamlit dashboard |
| Recommended | Sentinel-5P satellite data + Uncertainty (conformal prediction) + Personalization |
| If time remains | GNN, TFT, live traffic, real-time streaming, mobile app, SMS alerts, PostgreSQL+PostGIS, Docker |

# 10. Final Demonstration Flow

- 1. User selects a location

- 2. System finds nearby monitoring stations

- 3. Current PM2.5 / AQI is retrieved

- 4. Hyperlocal estimation (spatial model) fills the gap between stations

- 5. ML forecast produces Next 1h / 3h / 6h values with a prediction range and confidence

- 6. User profile is applied

- 7. Risk assessment is generated

- 8. Alert is triggered if needed

Core research question: Can we improve neighborhood-level short-term PM2.5 forecasting by combining sparse ground observations with weather, spatial information and satellite observations, while also communicating prediction uncertainty and personalized risk?

# 11. Final Recommended Stack (3-person team)

| Layer | Choice |
| --- | --- |
| Data | CPCB/India OGD + OpenAQ + Open-Meteo + Sentinel-5P + OpenStreetMap |
| ML | XGBoost → LSTM |
| Spatial | IDW → Kriging |
| Uncertainty | Conformal Prediction |
| App / Dashboard | Streamlit + Folium / Plotly |
| Storage | Parquet / SQLite (upgrade to PostgreSQL+PostGIS only if time remains) |
| Deployment | Optional — only if time remains |
| Primary target | PM2.5 |
| Forecast horizon | 1–6 hours |
| Study area | One Indian city, initially |

This scope stays ambitious enough to impress while remaining realistically finishable by a 3-person team within a 20-week timeline.